## 1. Summary
VINDHYA Climate Intelligence Portal
Weekly progress report ¦ 1 August 2026 to 6 August 2026 ¦ 63 commits over 6 days
Metric | Value | Note
Project start | 1 August 2026 | First commit: repository upload
Days elapsed | 6 | 1 Aug to 6 Aug 2026
Total commits | 63 | 28 on day 1, 13 on day 2, 8 on day 3, 12 on day 6
Live site | GitHub Pages | vindhyaresearch25-a11y.github.io/vindhya-climate-portal/dashboard/
States and UTs covered | 36 of 36 | Complete
Districts covered (boundaries) | 733 of 733 | Complete
Blocks / Tehsils covered | 6,312 | Complete
Villages covered | 6,54,285 | Complete, zero-overlap verified
Climate indices computed | 196 of 733 districts | 27 percent. Running state by state.
Village profiles | 6,49,719 villages | 46 attribute columns retained
Mandi price coverage | 733 districts | Refreshed daily, automated
Crop statistics | 733 districts | Refreshed monthly, automated
Repository data size | 802 MB | Boundaries 650 MB, profiles 102 MB, crop yield 47 MB
GitHub Pages limit | 1 GB | 80 percent consumed
Storage decision | Hugging Face Datasets | Free, no payment card, CORS and Range verified
Chatbot backend | Cloudflare Worker | Live. API key never reaches the browser.

## 2. Data sources
Data sources and their status
Every source is a published government or scientific dataset. Nothing is generated.
Dataset | Source organisation | Access method | Coverage achieved | Status
Administrative boundaries | Survey of India, via NWDP (Ministry of Jal Shakti) | Free download, no login | 36 states, 733 districts, 6,312 blocks, 6,54,285 villages | Complete
Village profiles | Survey of India attribute table (same source) | Free download | 6,49,719 villages, 46 columns | Complete
Climate: temperature | ERA5-Land, ECMWF via Google Earth Engine | GEE service account | 196 of 733 districts | In progress
Climate: rainfall | CHIRPS, UCSB via Google Earth Engine | GEE service account | 196 of 733 districts | In progress
Mandi prices | AGMARKNET, Ministry of Agriculture, via data.gov.in | Public API, registered key | 733 districts, daily | Automated
Crop statistics | Ministry of Agriculture, via data.gov.in | Public API, paginated | 733 districts, monthly batches | Automated
Crop yield | Ministry of Agriculture district series | Public API | District level | Complete
NDVI | UNDP DiCRA (MODIS derived) | Published dataset | 52 Madhya Pradesh districts | Partial
Projections to 2050 | NASA NEX-GDDP-CMIP6 via Google Earth Engine | GEE service account | Workflow written, not yet run nationally | Pending
Soil moisture | SMAP via Google Earth Engine | GEE service account | Not yet integrated | Pending
Forest cover | Forest Survey of India, and Hansen GFC via GEE | Report download plus GEE | Not yet integrated | Pending
Groundwater | Central Ground Water Board, India-WRIS | To be assessed | Not yet integrated | Pending
Live weather | NASA POWER | Free API, no key required | Not yet integrated | Pending
Cadastral parcels | Madhya Pradesh Bhulekh, Revenue Department | Institutional request required | Deliberately disabled | Blocked
Chatbot inference | Cloudflare Workers AI (Llama 3.2 3B) | Worker binding, key in secret | Live | Complete

## 3. Work completed
What was completed this week
Grouped by area. Every item is verified on the live site or in the repository.
Area | Work item | Outcome
Data integrity | Removed 50 synthetic districts and about 5,000 generated villages | Fabricated data eliminated from the pipeline
Data integrity | Removed invented cadastral parcels with fictional owner names | Cadastral panel disabled pending official records
Data integrity | Removed hardcoded risk, drought, heat and NDVI values | All figures now read from data files
Data integrity | Removed the fixed 94.2 percent accuracy claim | Unsupported claim gone
Data integrity | Removed fabricated advisory examples and map risk circles | No invented advisories remain
Data integrity | Continuous integration now fails the build on random number generation | Fabrication cannot re-enter the pipeline
Boundaries | Replaced community boundary files with Survey of India data | Officially sourced boundaries nationwide
Boundaries | Built state, district, block and village layers for all 36 states and UTs | 6,54,285 village polygons
Boundaries | Switched to topology-preserving simplification | Zero overlapping polygons, verified pair by pair nationwide
Boundaries | Fixed marker placement to use the drawn polygon | Pin now falls inside the selected village
Coverage | Extended mandi price fetching from 5 to 733 districts | Daily national coverage, automated
Coverage | Extended crop statistics to 733 districts | Monthly batches, automated
Coverage | Computed climate indices for 196 districts | 27 percent of the country, continuing
Coverage | Built village profile layer for 6,49,719 villages | 46 attribute columns, 102 MB after encoding
Interface | Removed all AI branding from titles, buttons and navigation | Named by task, not by tool
Interface | Removed all 92 emoji, replaced with a single icon set | Zero emoji remain
Interface | Self-hosted the Inter typeface, collapsed to a six-step scale | Consistent rendering across operating systems
Interface | Reverted the dark theme after reviewing reference portals | Single light theme throughout
Interface | Rebuilt the landing page around three coverage tiers | Boundary, observed and projected stated separately
Interface | Fixed three overlapping map controls | North arrow, scale bar and legend no longer collide
Interface | Consolidated two clocks into one, added a government identity footer | Source attribution now visible
Interface | Added responsive layouts for laptop, tablet and mobile | Usable on a farmer's phone
Interface | Moved render-blocking scripts out of the document head | Fixed the 30 second blank page
Chatbot | Renamed to Kisan Sahayak | Task-named, bilingual
Chatbot | Built a Cloudflare Worker proxy | API key never reaches the browser
Chatbot | Added origin allowlist and rate limiting | Only this portal can use the endpoint
Chatbot | Switched to Cloudflare Workers AI after the Gemini quota was exhausted | Six model fallback chain, free tier
Infrastructure | Set up Google Earth Engine service account access | Verified with a real Sentinel-2 query
Infrastructure | Wrote a resumable Colab notebook for national computation | Runs on Google servers, not the laptop
Infrastructure | Evaluated Cloudflare R2 and rejected it | Required a payment card
Infrastructure | Verified Hugging Face Datasets as the storage target | CORS and Range requests both confirmed working
Infrastructure | Resolved the macOS file permission block | Repository access restored
Documentation | Wrote ten standing orders into CLAUDE.md | Read automatically at the start of every session
Documentation | Maintained a provenance register in DATA_SOURCES.md | Every served file has a source row
Documentation | Wrote a four-stage research paper review workflow | Reviewer findings are verified, not accepted blindly

## 4. Pending
What remains
Ordered by priority. Storage must be resolved before village-level computation begins.
Priority | Work item | Why it matters | Blocked by
1 | Move boundaries and village profiles to Hugging Face | Repository is at 80 percent of the GitHub Pages limit | Nothing, ready to start
1 | Introduce a single DATA_BASE_URL configuration | Storage can then move without touching fifty files | Nothing
2 | Remove the count-up animation, 12 instances remain | The page shows wrong numbers for the first few seconds | Nothing
2 | Move 192 inline styles into CSS variables | One change should propagate portal wide | Nothing
3 | Compute climate indices for the remaining 537 districts | Currently 196 of 733 | Running, continues automatically
3 | Compute village-level indices nationwide | The core promise of the platform | Storage must be resolved first
3 | Extend NDVI to all four levels nationwide | Currently 52 Madhya Pradesh districts only | Storage
3 | Build the agricultural advisory layer | Derived from climate and NDVI | Both inputs must exist first
4 | Add the basemap switcher with five basemaps | Boundary colours must invert on light basemaps | Nothing
4 | Add PNG export at publication resolution | Needed for the research paper | Nothing
4 | Build the multi-select comparison view | State and district comparison, FAOSTAT style | Nothing
5 | Add the Kisan Sahayak welcome popup | Farmers need to know what to ask | Nothing
5 | Connect the free research paper APIs | OpenAlex, Semantic Scholar, CORE, CrossRef, FAO AGRIS, ICAR KRISHI | Nothing
5 | Complete the twenty panel source audit | Soil moisture, groundwater, forest and weather panels are still empty | Nothing
6 | Write the methodology literature review | Required before publication | Nothing
6 | Run CMIP6 projections to 2050 nationally | Currently a labelled OLS trend, not a projection | GEE compute budget
6 | Complete the security hardening | Secret scanning, pre-commit hook, key rotation | Owner must revoke three exposed keys

## 5. Timeline
Day by day
Commit counts are from the repository history.
Date | Commits | Main work
1 Aug 2026 | 28 | Repository restructured. Synthetic data removed. Site deployed to GitHub Pages. Ten standing orders written into CLAUDE.md.
2 Aug 2026 | 13 | Survey of India boundaries built for all 36 states and UTs. Topology-preserving simplification fixed the overlap defect. Mandi and crop statistics extended to 733 districts. Village profile layer built for 6,49,719 villages.
3 Aug 2026 | 8 | Google Earth Engine access verified. Colab notebook written. Landing page rebuilt around three coverage tiers. Marker placement bug fixed.
4 Aug 2026 | 1 | Automated data refresh only.
5 Aug 2026 | 1 | Automated data refresh only.
6 Aug 2026 | 12 | Cloudflare Worker deployed for the chatbot. Dark theme reverted to light. Responsive layouts added. Storage evaluated: R2 rejected for requiring a card, Hugging Face verified and adopted.
Note
Commit counts measure activity, not value. Day 2 produced the boundary layer for the entire country, which is the single largest asset in the project.

## 6. Risks
Open risks and decisions taken
Recorded so that the reasoning survives beyond this week.
Item | Position taken | Reasoning
IMD gridded data | Not available on this machine | The raw NetCDF was verified absent on 2 August. ERA5-Land and CHIRPS were substituted with the owner's approval, and every output file states this. It is never presented as IMD data.
Storage beyond 1 GB | Hugging Face Datasets | Cloudflare R2 required a payment card and authorisation to charge beyond free limits. Hugging Face is free, requires no card, and verified working for both CORS and Range requests.
Data volume | Reduce before buying | The projection is 5.4 GB. Positional-array encoding already reduced village profiles from 665 MB to 102 MB. The same technique should be measured on climate before any storage is purchased.
API keys in the browser | Never | A static site exposes anything in its JavaScript. The Cloudflare Worker holds the key. Two keys have already leaked during this project.
Exposed credentials | Three require revocation | A GitHub personal access token, a Gemini key, and a Hugging Face token have each appeared in plain text. All three should be deleted and reissued.
Scraping government portals | Refused | Only machine-readable endpoints the publisher provides are used. e-NAM and e-CHARAK are cited as portal pointers rather than scraped.
Sci-Hub for literature | Refused | It hosts pirated material. Eight free and lawful APIs cover the same ground with wider reach.
Observed against projected | Always separated | CMIP6 output is a scenario, not an observation. Mixing them would not survive peer review.
Missing data | Stated, never filled | Where no value exists the portal says so. A neighbouring unit's figure is never substituted.

## 7. Master prompt
Master prompt for Claude Code
Paste the block below into Claude Code. The same text is kept in the repository as FINAL_PROMPT.md so it survives between sessions.
Paste this to start:
Padho: FINAL_PROMPT.md -- poori nayi hai, aaj ki naapi hui sthiti ke saath.
Phase 1 (Hugging Face storage) se shuru karo, phir kram se aage.
Sab tum karo -- command mujhe dekar mat baithna, khud chalao.
Har item ke saamne HUA / NAHI KIYA / kyun nahi likho.
Full text of FINAL_PROMPT.md
VINDHYA -- MASTER PLAN (2026-08-06)
Poore desh ka, teenon parat, chaaron star par:
Climate Risk + Satellite NDVI + Agricultural Advisory
36 States/UTs · 733 Districts · 6,312 Blocks/Tehsils · 6,54,285 Villages
Kram se karo, upar se neeche. Beech me mat poochho -- sirf asli gadbad
par ruko. Har item ke saamne likho: **HUA / NAHI KIYA / kyun nahi**
**Sab tum karo.** Main sirf wahi karunga jo tum nahi kar sakte (browser
me click, key revoke) -- aur uske liye ek-ek click alag batana.
---
AAJ KI ASLI STHITI (naapi hui, anuman nahi)
¦ ¦ ¦
¦---¦---¦
¦ Project shuru ¦ 1 Aug 2026, 63 commit, 6 din ¦
¦ Boundaries ¦ 36 rajya, 733 zile, 6,312 block, 6,54,285 gaon -- **POORA** ¦
¦ Village profiles ¦ 6,49,719 gaon, 46 column -- **POORA** ¦
¦ Climate indices ¦ **196 / 733 zile** (27%) ¦
¦ Mandi prices ¦ 733 zile, roz apne aap ¦
¦ Crop statistics ¦ 733 zile, mahine me ¦
¦ Repo data ¦ **802 MB / 1 GB** -- 80% bhar chuka ¦
¦ Chatbot ¦ Cloudflare Worker chalu, Workers AI (Llama 3.2 3B) ¦
¦ Storage ¦ Hugging Face verify ho chuka -- CORS aur Range dono ¦
---
PHASE 1 -- STORAGE (turant, warna baaki ruk jayega)
Repo 802 MB par hai, seemaa 1 GB. Village-level computation ka nateeja
rakhne ki jagah nahi bachegi. Isliye yahi pehle.
Hugging Face taiyaar hai:
Repo : vindhyaresearch/vindhya-climate (dataset, public)
Base : https://huggingface.co/datasets/vindhyaresearch/vindhya-climate/resolve/main/
Token : HF_TOKEN environment me hai -- chat me KABHI mat maango
CORS : verified, exact origin allow hai
Range : accept-ranges: bytes -- PMTiles yahan CHALEGA
Limit : 3000 request prati 5 minute -- isliye block-war files
1.1 `config/data_config.json` banao:
{ "DATA_BASE_URL": "https://huggingface.co/datasets/vindhyaresearch/vindhya-climate/resolve/main/" }
Har loader yahi padhega. URL kahin aur hardcode NAHI.
1.2 `boundaries/` (650 MB) HF par bhejo, phir `village_profiles/`
(102 MB). `huggingface_hub` ka `upload_folder` use karo.
Har rajya ke baad progress batao.
1.3 HF wali files se portal **chalta hua SCREENSHOT** do -- map par
boundary render hoti hui, chaaron star par.
**Tab tak repo se purani files MAT hatao.**
1.4 Chalti hui dikh jaye tabhi repo se hatao. Repo ~50 MB reh jayega.
1.5 **File ka dhancha** -- ek badi file KABHI nahi:
climate¦ndvi¦advisory/
state/<state>.json
district/<state>/<district>.json
block/<state>/<district>.json
village/<state>/<district>/<block>.json
Village file **BLOCK-war**. Gaon-war KABHI nahi -- rate limit takrayegi.
1.6 **PMTiles ab mumkin hai.** Naapo: boundaries ko PMTiles me badalne se
kul size kitna ghatta hai, aur ek visitor jo EK gaon dekhta hai kitna
MB kheenchta hai. **Asli number batao, faisla mat lo.**
1.7 **Data chhota karo** -- positional-array encoding ka prototype banao,
jaisa `village_profiles` me kiya tha (665 MB -> 102 MB, 6.5 guna kam).
Ek zile ka climate data dono roop me likho, asli size ka farak batao.
Padhne me kitna dhima hua, wo bhi.
1.8 `docs/DATA_SOURCES.md` me likho konsa data ab HF par hai aur kyun.
1.9 Git LFS KABHI nahi. Har file 100 MB se kam.
---
PHASE 2 -- BACHE HUE UI KAAM
2.1 **`data-target` 12 jagah hai** -- count-up animation abhi bhi chalti
hai. Pehle kuch second galat number dikhta hai. Koi screenshot le le
to galat aankda uske paas chala jayega. Attribute aur animation dono
hatao. Pehle frame se asli number.
2.2 **Inline `style=""` 192 bache** -- CSS variables me lao.
Rang, spacing, font-size, radius, border. Ek jagah badlo, poore
portal me badle.
2.3 **"AI chatbot" shabd 1 jagah bacha hai** -- hatao.
2.4 **Rang -- LIGHT hi rahega**
--bg #FFFFFF · --bg-soft #F5F7FA · --border #D8DEE7
--text #1A2332 · --text-muted #5A6A7A · --accent #2D8F5C
Khatra ke rang sirf DATA ke liye:
extreme #B02418 · high #D9822B · moderate #E0B84C · low #3E9C5A
Gradient, neon, glow -- kabhi nahi.
2.5 **Spacing** 4px grid: 4/8/12/16/24/32/48. Iske bahar kuch nahi.
2.6 **Card** ek shakal ke: radius 6px, border 1px, shadow nahi.
label (chhota, gaun) -> VALUE (bada, tabular) + unit -> trend
-> "Source: <naam>, <date>"
2.7 **Chart** -- Chart.js ka default look hatao. Halki horizontal grid,
vertical nahi. Line 2px, point sirf hover par. Axis par unit.
Neeche source aur date.
2.8 **State** teeno: loading (skeleton), empty ("Is jagah ka aankda abhi
uplabdh nahi hai" + kyun), error (kya hua + retry button).
2.9 **Landing background** -- do slide, 8 second par halka fade:
Slide 1 asli Indian kisan khet me, Slide 2 precision farming /
satellite se khet. Photo poori chaudai, opacity 1, scrim sirf text
ke peechhe. Licence saaf: PIB / ICAR / Unsplash / apni photo.
Google se uthai photo KABHI nahi. Har photo par credit.
2.10 **Sarkari pehchaan** neeche patti me:
Boundaries: Survey of India ¦ Climate: ERA5-Land + CHIRPS via GEE
¦ Projections: NEX-GDDP-CMIP6 ¦ Market: AGMARKNET, data.gov.in
Last updated: <asli date, file se>
Indicative, not for legal or cadastral use
---
PHASE 3 -- BASEMAP + EXPORT
3.1 **Basemap switcher** -- paanch, aur koi nahi:
Satellite (Esri World Imagery), Street (OSM), Terrain (OpenTopoMap),
Light (Carto Positron), Dark (Carto Dark Matter).
Har ek ka attribution dikhe.
3.2 **Boundary ka rang apne aap badle** -- sabse zaroori hissa
Gehre basemap (Satellite/Dark/Terrain) -- casing:
kaala underlay weight+3 opacity 0.6, upar chamakdaar line
State #FF9500 w4 · District #00E5FF w3 · Block #FF3DFF w2.5
· Village #C6FF00 w2
Halke basemap (Street/Light) -- ULAT karo:
safed underlay, upar gehri line
State #B45309 w4 · District #0E7490 w3 · Block #A21CAF w2.5
· Village #4D7C0F w2
Har basemap par khud screenshot lekar dikhao ki chaaron star saaf
dikh rahe hain.
3.3 **Export as PNG** -- map ke kone me button. Nikli image me ho:
basemap + saari dikhti boundary, legend, scale bar, north arrow,
chuni jagah ka poora naam (India > State > District > Block >
Village), source + tareekh, portal ka naam.
Kam se kam 2000px chaudai -- research paper ke layak.
"Copy to clipboard" bhi. Mobile par gallery me save ho.
---
PHASE 4 -- MULTI-SELECT COMPARE (sirf sidebar me)
Mukhya Location Selector par KOI asar nahi. Bilkul alag feature.
- Sidebar me item "Compare"
- Ek star chuno (State/District/Block/Village), phir 2 se 6 jagah,
search ke saath (733 zile me dhoondhna aasan ho)
- Har jagah ka apna rang -- wahi rang map, table, chart teenon me
- **Map:** sab ek saath highlight, label ke saath, apne aap zoom
- **Table** (FAOSTAT / UNDP HDR jaisa): row = jagah, column = index
Heatwave days, SPI, Rainfall, Rx1day, NDVI, Population,
Net area sown, Irrigated area
Har column par sort. Sabse ooncha/neecha halka highlight.
Data na ho to "Data not available" -- khali ya zero nahi, aur aurat
me mat gino. Har column ke neeche source aur saal.
Saal ka slider (2000-2024), table saath me badle.
- **Chart:** grouped bar (saal ke hisaab se) + line chart (samay ke
hisaab se, har jagah ki apni line apne rang me)
- **Nikalo:** table -> CSV/XLSX, chart -> PNG, map -> PNG.
Har file me source, tareekh, shreya.
- **Mobile:** table ko horizontal scroll me mat daalo -- har jagah ka
ek card, ek ke neeche ek. 3 se zyada jagah nahi.
---
PHASE 5 -- KISAN SAHAYAK
Naam ho chuka. Worker chal raha hai:
POST https://vindhya-gemini-proxy.vindhyaresearch25.workers.dev
{"prompt": "<ek string>"} -> {"text": "...", "source": "..."}
Workers AI (Llama 3.2 3B), chhe model ki fallback suchi.
Gemini ka quota khatam. Key sirf Worker ke secret me -- browser me KABHI
nahi.
5.1 **Pehla popup** (pehli baar kholne par)
"नमस्ते, मैं किसान सहायक हूँ" / "Namaste, I am Kisan Sahayak"
"अपने गाँव की खेती, मौसम, फ़सल या मंडी भाव से जुड़ा कोई भी सवाल पूछिए।"
Chaar chip -- hardcode NAHI, chuni jagah aur mausam ke hisaab se:
"इस साल बारिश कैसी रही?" · "मेरे गाँव में कौन सी फ़सल ठीक रहेगी?"
· "आज मंडी में भाव क्या है?" · "सूखे का ख़तरा कितना है?"
Neeche: "जवाब असली सरकारी आँकड़ों से। जहाँ आँकड़ा नहीं है, वहाँ साफ़ बता
दिया जाएगा।"
Ek hi baar dikhe (localStorage), phir chhota button.
Mobile par neeche se aaye, poori screen na dhake.
5.2 **Jawab ka niyam**
- Prompt me PEHLE asli aankde daalo, phir sawal
- Chuni jagah ke chaaron star ka data fetch karo
- Fasal ke hisaab se
- Model ko saaf likho: *"Sirf diye gaye aankdon se jawab do. Koi number
khud mat banao. Jahan aankda na ho, kaho ki uplabdh nahi hai. Saral
bhasha, kisan ke liye."*
- Har jawab ke neeche source aur tareekh
- Data na ho: "इस जगह का आँकड़ा अभी उपलब्ध नहीं है"
- Jis bhasha me sawal, usi me jawab
5.3 **Research papers** -- in FREE API se jodo:
OpenAlex, Semantic Scholar, CORE, CrossRef, DOAJ, PubMed/PMC,
FAO AGRIS, ICAR KRISHI
Har jawab ke saath title, lekhak, saal, link.
**Sci-Hub kabhi nahi** -- pirated hai, sarkari portal par kanooni
khatra.
---
PHASE 6 -- DATA, POORE DESH KA (saath-saath chalta rahe)
6.1 **Chaaron star ka hisab**
Village -> apne pixel se (`docs/METHODOLOGY.md` wali methodology)
Block -> uske gaon ka aggregate
District -> uske block ka aggregate
State -> uske zilon ka aggregate
Har aggregate ke saath: **kitne units se bana + standard deviation**.
Sirf mean KABHI nahi.
6.2 **Climate** -- 196/733 zile ho chuke, 537 baaki.
District-level chalta rahe (sirf 3 MB, koi dikkat nahi).
Village-level Phase 1 ke BAAD.
6.3 **NDVI** -- abhi sirf 52 MP zile (DiCRA). MODIS/Sentinel-2 (GEE) se
poore desh me, chaaron star par.
6.4 **Advisory** -- upar ke dono se vyutpann, chaaron star par.
6.5 **EK RAJYA CHALAKAR NAAPO** -- poore desh se pehle
Madhya Pradesh, village-level, teenon parat. Phir ASLI batao:
- kitne gaon, kitna MB, kitna samay
- 6,54,285 gaon ka sudhra anuman
- ek visitor jo EK gaon dekhta hai kitna MB kheenchta hai
- GEE ka EECU kitna khapa
**In chaar jawab ke baad hi baaki 35 rajya.**
6.6 **Validation** -- CHIRPS aur ERA5 ko IMD ki JAANCH ke liye, badle me
nahi. Har zile ke liye: dono ka maan, correlation, bias.
`data/validation/<state>/<district>.json`, alag panel.
Research paper me ye majboot baat mani jaati hai.
6.7 **Niyam**
- Jis gaon ka pixel na mile -> "data not available".
Paas wale gaon ka maan KABHI nahi.
- Observed (ERA5/CHIRPS), projected (CMIP6) aur validation -- teeno
ALAG, kabhi mila kar nahi
- Har file me metadata: source, method, baseline, unit count, date,
checksum
- Har rajya ke baad upload + `NIGHT_LOG.md`: samay, size, gaon, kya
chhoota
- GEE ka EECU quota paas aaye to RUKO aur batao
---
PHASE 7 -- 20 PANEL KA SOURCE AUDIT
¦ Panel ¦ Source ¦ Abhi ¦
¦---¦---¦---¦
¦ Climate Risk Atlas / Heat Waves / Extreme Precip / Drought ¦ apne computed indices ¦ 196 zile ¦
¦ Rainfall Monitor ¦ CHIRPS (GEE) ¦ 196 zile ¦
¦ NDVI Analytics ¦ MODIS/Sentinel-2 (GEE) + UNDP DiCRA ¦ 52 MP zile ¦
¦ Crop Health ¦ Sentinel-2 EVI/NDVI (GEE) ¦ nahi ¦
¦ Soil Moisture ¦ SMAP (GEE) ¦ **khali** ¦
¦ Forest Monitor ¦ FSI ISFR + Hansen/GFC (GEE) ¦ nahi ¦
¦ Satellite Viewer ¦ GEE + Bhuvan (ISRO) WMS ¦ nahi ¦
¦ Live Weather ¦ NASA POWER (free, no key) ¦ nahi ¦
¦ Groundwater ¦ CGWB / India-WRIS ¦ **khali** ¦
¦ Village Profile ¦ SoI attribute table ¦ **HO CHUKA** ¦
¦ Mandi Prices ¦ AGMARKNET via data.gov.in ¦ **HO CHUKA** ¦
¦ Crop Statistics ¦ data.gov.in MoA&FW ¦ **HO CHUKA** ¦
¦ Panchayat Dashboard ¦ LGD + eGramSwaraj ¦ nahi ¦
¦ PMFBY Insurance ¦ pmfby.gov.in ¦ nahi ¦
¦ Trend Forecast ¦ apne data par OLS, "indicative" label ¦ hai ¦
¦ Biodiversity Risk ¦ ENVIS / India Biodiversity Portal ¦ nahi ¦
¦ Cadastral Map ¦ MP Bhulekh -- band hai, band rahe ¦ band ¦
Har panel ke liye:
1. Public API hai ya nahi -- pehle data.gov.in, phir uski apni site
2. API hai -> jodo (script + GitHub Actions schedule + metadata)
3. API nahi, bulk CSV/PDF hai -> utaro aur convert karo
4. Kuch bhi machine-readable nahi -> panel me SAAF likho:
*"No public API. Source: <naam>, <link>. Institutional data request
required."* Khali ya toota mat chhodo.
**Scraping ka niyam:** sarkari dashboard scrape MAT karo. Sirf wahi lo
jo publisher ne machine-readable diya ho -- API, CSV, bulk download,
WMS/WFS. Terms mana karein to panel me wahi likho. Ye e-NAM aur
e-CHARAK par pehle tay ho chuka hai -- wahi niyam sab par.
**Har panel me dikhe:** source ka naam + link, data ki tareekh, spatial
unit + resolution, "Last updated", method ka link.
**Report:** table -- panel ¦ source ¦ API hai? ¦ INTEGRATED /
NO PUBLIC API / PENDING ¦ kya chahiye aage badhne ke liye
---
PHASE 8 -- METHODOLOGY (research papers)
Free API: OpenAlex, Semantic Scholar, CrossRef, CORE, NASA ADS.
**Vishay** (peer-reviewed, high-impact only):
- NEX-GDDP-CMIP6 downscaling (NASA) -- dataset ka apna paper
- Bias correction: quantile mapping / delta change -- India ke monsoon
ke liye kaunsa theek hai
- ETCCDI extreme indices ki manak paribhasha
- SPI ki ganana aur zero-inflated gamma sudhaar
- **ERA5-Land aur CHIRPS ki India ke liye validation studies**
(ye sabse zaroori -- hum yahi data istemal kar rahe hain)
- Heatwave definition -- IMD ka aur international ka farak
- IPCC AR6 WG1 Ch.11 (extremes) -- projection dikhane ka tarika
- Village-level downscaling ki seemaa
**Patrikaayein:** Nature Climate Change, Journal of Climate, Climate
Dynamics, ERL, IJoC, Theoretical and Applied Climatology, Current
Science, MAUSAM (IMD), Copernicus open journals (ESD, HESS, NHESS)
Likho aur commit karo:
- `docs/references/` -- har paper ki BibTeX + PDF link
- `docs/METHODOLOGY_REVIEW.md` -- har method ke liye: kaunsa tarika
chuna, KYUN, kis paper ke aadhar par, uski seemaa, kis paper ne alag
raay di
Agar pata chale ki mojooda method me kuch galat ya purana hai -- **RUKO
aur batao**. Chupchap mat badlo, aur galat jaan kar chalne bhi mat do.
---
PHASE 9 -- SECURITY
9.1 Repo aur **POORI git history** me key dhoondho:
ghp_ github_pat_ AIza hf_ sk- sk-ant- -----BEGIN
"api_key" "apiKey" "token" "secret" "password"
Jo mile uski file, line, commit batao. **Chupchap mat hatao** --
history se hatane par sabko dobara clone karna padta hai.
9.2 `.gitignore` majboot: `.env .env.* *.pem *.key`
`service-account*.json gee_key*.json *credentials*.json .wrangler/`
Aur pre-commit hook jo key jaisa string mile to commit roke.
9.3 CI me secret scanning job -- mile to build FAIL.
9.4 GEE key `~/.gee/service-account.json` repo me kabhi na jaye.
9.5 `docs/SECURITY.md` -- konsi key kahan rehti hai, kaise rotate karni
hai, leak ho jaye to kya karna. **Key ka maan kabhi nahi**, sirf
jagah aur tarika.
Malik ko khud karna hai (teen key ab tak khuli hain):
- Purani Gemini key delete (gen-lang-client-0298941748)
- Purana GitHub PAT delete (ghp_bzBq...)
- Hugging Face token delete aur naya banao (hf_REE... chat me aa chuka)
- GitHub -> Settings -> Code security -> Secret scanning aur Push
protection dono ON
---
NIYAM -- sab par lagu
- **Koi banaya hua aankda nahi.** Har number asli file se gina jayega
- **Layout aur panel ki jagah wahi rahegi**
- **Portal LIGHT hai aur light hi rahega**
- Observed / projected / validation -- teeno ALAG, kabhi mila kar nahi
- Jahan data nahi: "data not available" + KYUN. Paas wale unit ka maan
KABHI nahi
- Har phase ke baad commit + push
- Har item ke saamne: HUA / NAHI KIYA / kyun nahi
- Repo 1 GB paas aaye to RUKO aur vikalp do -- khud faisla mat lo
- Sarkari dashboard scrape MAT karo
- Key chat me KABHI mat maango
---
AAKHIR ME -- LIVE site par KHUD khol kar screenshot do
- Landing (dono slide), photo saaf dikhti hui
- Dashboard: paanchon basemap par
- Chaudai: 1512px, 820px, 390px, 320px
- Simrol (Mhow, Indore) -- pin peele polygon ke ANDAR
- Kisi doosre rajya ka gaon (Tamil Nadu ya Assam)
- Compare table (4 zile)
- Export ki hui PNG
- Kisan Sahayak ka popup aur ek asli jawab
Phase 1 se shuru karo.